## Efforts Utilization
| Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Names of Resource | time axis 2017-12-27 to 2018-06-02
Kunal Kotadia | Absent | Absent | Absent | Absent |  | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management |  | Project Management | Project Management | Project Management | Project Management | Project Management |  |  | Project Management | Project Management | Project Management | Project Management |  |  |  | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management |  | Project Management | Project Management | Project Management | Project Management | Project Management |  |  | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management |  | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management |  | Project Management | Project Management | Project Management | Project Management |  |  |  | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management |  | Project Management | Project Management | Project Management | Project Management | Project Management |  |  | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management |  | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management |  | Project Management | Project Management | Project Management | Project Management | Project Management |  |  | Project Management | Absent | Project Management | Project Management | Project Management | Project Management |  | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management |  | Project Management | Project Management | Project Management | Project Management | Project Management |  |  | Absent |  | Project Management | Project Management | Project Management |  |  | Project Management | Project Management | Project Management | Project Management | Project Management |  |  | Project Management | Project Management | Project Management | Project Management | Project Management | Project Management |  | Project Management | Not on Project | Not on Project
Krishnan V | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Absent | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Review-Rework | Review-Rework | Review-Rework | Requirement-Rework | Requirement-Rework |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Leakage | Leakage | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Leakage | Execution R1 |  |  |  | Execution R1 | Absent | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project |  | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project
Urvang D | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Absent | Absent | Absent | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Review-Rework | Review-Rework | Review-Rework | Requirement-Rework | Requirement-Rework |  |  | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework |  |  |  | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework |  | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework |  |  | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework |  | Requirement-Rework | Review-Rework | Review-Rework | Leakage | Leakage | Leakage |  | Review-Rework | Leakage | Leakage | Execution R1 |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R1 | Leakage | Execution R1 | Execution R2 | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  | Absent | Absent | Absent | Execution R2 | Execution R2 |  |  | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Regression Testing | Regression Testing | Regression Testing | Regression Testing |  | Regression Testing | Project Management | Project Management
Tushar V | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Review-Rework | Review-Rework | Review-Rework | Requirement-Rework | Requirement-Rework |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Leakage | Leakage | Leakage | Leakage |  | Execution R1 | Leakage | Leakage | Absent |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Absent | Absent | Absent | Absent | Absent |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R1 | Leakage | Execution R1 | Execution R2 | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Regression Testing | Regression Testing | Regression Testing | Regression Testing |  | Regression Testing | Regression Testing | Regression Testing
Shubhangi S | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Review-Rework | Review-Rework | Review-Rework | Absent | Requirement-Rework |  |  | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework |  |  |  | Absent | Absent | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework |  | Execution R1 | Execution R1 | Requirement-Rework | Requirement-Rework | Requirement-Rework |  |  | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework |  | Requirement-Rework | Review-Rework | Leakage | Leakage | Leakage | Leakage |  | Review-Rework | Leakage | Leakage | Execution R1 |  |  |  | Absent | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R2 | Execution R2 | Execution R2 | Leakage | Execution R2 |  |  | Execution R2 | Execution R1 | Leakage | Execution R1 | Execution R2 | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 |  |  | Absent | Absent | Absent | Absent | Absent |  |  | Execution R2 | Execution R2 | Absent | Regression Testing | Regression Testing | Regression Testing |  | Regression Testing | Regression Testing | Regression Testing
Yogesh K | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Review-Rework | Review-Rework | Review-Rework | Requirement-Rework | Requirement-Rework |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Review-Rework | Leakage | Leakage | Leakage |  | Execution R1 | Leakage | Leakage | Execution R1 |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R2 | Leakage | Execution R2 |  |  | Execution R2 | Execution R1 | Leakage | Execution R1 | Execution R2 | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Regression Testing | Regression Testing | Regression Testing | Regression Testing |  | Regression Testing | Regression Testing | Regression Testing
Tarandeep K | Not on Project | Not on Project | Not on Project | Not on Project |  | Shadow | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Absent |  | Review-Rework | Review-Rework | Review-Rework | Requirement-Rework | Requirement-Rework |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Absent | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Leakage | Leakage | Leakage | Leakage |  | Execution R1 | Leakage | Leakage | Execution R1 |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Absent | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Absent | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R2 | Leakage | Execution R2 |  |  | Execution R2 | Execution R1 | Leakage | Execution R1 | Execution R2 | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Absent | Absent | Absent | Absent | Absent |  |  | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project
Neha S | Not on Project | Not on Project | Not on Project | Not on Project |  | Shadow | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Review-Rework | Review-Rework | Review-Rework | Requirement-Rework | Requirement-Rework |  |  | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework |  |  |  | Review-Rework | Review-Rework | Review-Rework | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Leakage | Leakage | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Leakage | Execution R1 |  |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project |  | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project
Vipul P | Not on Project | Not on Project | Not on Project | Not on Project |  | Shadow | Shadow | Shadow | Shadow | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Review-Rework | Review-Rework | Review-Rework | Requirement-Rework | Requirement-Rework |  |  | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Requirement-Rework |  |  | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework |  | Requirement-Rework | Review-Rework | Leakage | Leakage | Execution R1 | Execution R1 |  | Review-Rework | Leakage | Leakage | Execution R1 |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R2 | Execution R2 | Execution R2 | Leakage | Execution R2 |  |  | Execution R2 | Execution R1 | Leakage | Execution R1 | Execution R2 | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Execution R2 | Absent | Absent |  |  | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Not on Project | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Regression Testing | Regression Testing | Regression Testing | Regression Testing |  | Regression Testing | Regression Testing | Regression Testing
Shrutika | Not on Project | Not on Project | Not on Project | Not on Project |  | Shadow | Shadow | Shadow | Shadow | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  | Review-Rework | Review-Rework | Review-Rework | Requirement-Rework | Requirement-Rework |  |  | Review-Rework | Review-Rework | Review-Rework | Review-Rework |  |  |  | Review-Rework | Review-Rework | Review-Rework | Review-Rework | Review-Rework | Review-Rework |  | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation | Scenario Preparation |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Execution R1 | Execution R1 |  | Shadow | Shadow | Shadow | Shadow |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Absent | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R2 | Execution R2 | Execution R2 | Leakage | Execution R2 |  |  | Execution R2 | Leakage | Leakage | Leakage | Execution R2 | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 | Absent | Execution R2 | Execution R2 |  | Leakage | Leakage | Leakage | Execution R2 | Execution R2 |  |  | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project
Snehal | Not on Project | Not on Project | Not on Project | Not on Project |  | Shadow | Shadow | Shadow | Shadow | Shadow | Scenario Preparation | Scenario Preparation | Scenario Preparation | Shadow | Shadow | Shadow | Shadow | Scenario Preparation |  | Shadow | Shadow | Shadow | Requirement-Rework | Shadow |  |  | Shadow | Shadow | Shadow | Shadow |  |  |  | Review-Rework | Review-Rework | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R2 | Execution R2 | Execution R2 | Leakage | Execution R2 |  |  | Execution R2 | Leakage | Leakage | Leakage | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow |  | Shadow | Shadow | Shadow |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project
Natasha | Not on Project | Not on Project | Not on Project | Not on Project |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow |  |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R2 | Leakage | Execution R2 |  |  | Execution R2 | Execution R1 | Execution R1 | Execution R1 | Execution R2 | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Leakage | Leakage | Leakage | Execution R2 | Execution R2 |  |  | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 |  |  | Execution R2 | Execution R2 | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project
Niharika | Not on Project | Not on Project | Not on Project | Not on Project |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow |  |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow |  |  |  | Execution R1 | Absent | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Absent | Leakage | Absent | Absent | Absent |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project |  | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project
Devendra | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project |  |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework | Requirement-Rework |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow |  |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R2 | Leakage | Execution R2 |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project |  | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project
Karpaswamy Samy | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project |  |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Review-Rework | Review-Rework | Leakage | Leakage | Shadow | Shadow |  | Review-Rework | Review-Rework | Review-Rework | Execution R1 |  |  |  | Execution R1 | Execution R1 | Absent | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R2 | Leakage | Execution R2 |  |  | Execution R2 | Leakage | Leakage | Leakage | Execution R2 | Execution R2 |  | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  | Leakage | Leakage | Leakage | Execution R2 | Execution R2 |  |  | Execution R2 |  | Shadow | Shadow | Shadow |  |  | Execution R2 | Execution R2 | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project
Ahad | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project |  |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R2 | Leakage | Execution R2 |  |  | Execution R1 | Leakage | Leakage | Leakage | Execution R1 | Execution R1 |  | Execution R1 | Execution R2 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  | Leakage | Leakage | Leakage | Execution R2 | Execution R2 |  |  | Execution R1 |  | Shadow | Shadow | Shadow |  |  | Execution R2 | Execution R2 | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Regression Testing | Regression Testing |  | Regression Testing | Regression Testing | Regression Testing
Pooja | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project |  |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R2 | Leakage | Execution R2 |  |  | Execution R1 | Leakage | Leakage | Leakage | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow |  | Shadow | Shadow | Shadow |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project
Ashwini | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project |  |  |  | Not on Project | Not on Project | Not on Project | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R2 | Execution R2 | Execution R2 | Leakage | Execution R2 |  |  | Execution R1 | Leakage | Leakage | Leakage | Execution R1 | Absent |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow |  | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow
Komal | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project |  |  |  | Not on Project | Not on Project | Not on Project | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Execution R1 |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R2 | Absent | Absent | Leakage | Execution R2 |  |  | Execution R1 | Leakage | Leakage | Leakage | Execution R1 | Execution R1 |  | Execution R1 | Execution R2 | Execution R2 | Execution R2 | Execution R2 |  |  | Leakage | Leakage | Leakage | Execution R2 | Execution R2 |  |  | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project
Ashish | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project |  |  |  | Not on Project | Not on Project | Not on Project | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow |  |  |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  |  | Leakage | Execution R1 | Leakage | Execution R1 | Execution R1 | Execution R1 |  | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 | Execution R1 |  | Execution R2 | Execution R2 | Execution R2 | Leakage | Execution R2 |  |  | Execution R1 | Leakage | Leakage | Leakage | Shadow | Shadow |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow | Shadow | Shadow | Shadow | Shadow |  |  | Shadow |  | Shadow | Shadow | Shadow |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  |  | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project | Not on Project |  | Not on Project | Not on Project | Not on Project
Scenario Preparation | 5 | 5 | 5 | 5 | 0 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Execution R1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 5 | 5 | 5 | 6 | 6 | 6 | 0 | 6 | 7 | 6 | 6 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 5 | 5 | 0 | 0 | 4 | 4 | 0 | 5 | 0 | 0 | 9 | 0 | 0 | 0 | 16 | 15 | 16 | 17 | 17 | 17 | 0 | 16 | 0 | 17 | 17 | 17 | 0 | 0 | 0 | 14 | 0 | 17 | 17 | 17 | 0 | 17 | 16 | 16 | 16 | 16 | 16 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 1 | 7 | 3 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Review-Rework | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 2 | 0 | 0 | 0 | 0 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Requirement-Rework | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 1 | 1 | 2 | 2 | 3 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Discussion/Demo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Execution R2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 8 | 15 | 2 | 16 | 0 | 0 | 10 | 0 | 0 | 0 | 9 | 9 | 0 | 9 | 11 | 11 | 10 | 11 | 5 | 0 | 4 | 4 | 4 | 9 | 9 | 0 | 0 | 9 | 0 | 8 | 8 | 8 | 0 | 0 | 9 | 9 | 3 | 4 | 4 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leakage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 9 | 5 | 5 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 8 | 14 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Regression Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 6 | 6 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Management | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sign Off | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total-PLANNED | 5 | 5 | 5 | 5 | 0 | 5 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 9 | 10 | 10 | 10 | 10 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 17 | 16 | 17 | 18 | 18 | 18 | 0 | 17 | 18 | 18 | 18 | 18 | 0 | 0 | 18 | 15 | 19 | 18 | 18 | 18 | 0 | 18 | 17 | 17 | 17 | 17 | 17 | 0 | 17 | 16 | 16 | 17 | 17 | 0 | 0 | 16 | 15 | 16 | 16 | 13 | 12 | 0 | 12 | 12 | 12 | 11 | 12 | 6 | 0 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 11 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 10 | 4 | 5 | 5 | 0 | 0 | 6 | 6 | 5 | 6 | 7 | 7 | 0 | 7 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PHASE 1
Activity | 2017-12-27: Actual; 2017-12-28: Planned; 2017-12-29: Extra efforts spent; 2017-12-30: Requirment changes; 2017-12-31: Systems not delivered; 2018-01-01: Ideal time due to blocker issues / system down time; 2018-01-02: Multiple times defects retested - more than 3 rounds; 2018-01-03: Changes made in Test Cases due to Req. Changes during Execution
Scenario Preparation | 2017-12-27: 131; 2017-12-28: 116.5; 2017-12-29: 14.5; 2017-12-30: 14.5
Execution R1 | 2017-12-27: 514; 2017-12-28: 243.5; 2017-12-29: 270.5; 2017-12-30: 140; 2018-01-02: 100; 2018-01-03: 27.5
Review-Rework | 2017-12-27: 55; 2017-12-28: 0; 2017-12-29: 0
Requirement-Rework | 2017-12-27: 80; 2017-12-28: 0; 2017-12-29: 80; 2017-12-30: 80
Discussion/Demo | 2017-12-27: 0; 2017-12-28: 0; 2017-12-29: 0
Execution R2 | 2017-12-27: 237; 2017-12-28: 91.5; 2017-12-29: 145.5; 2017-12-30: 25; 2018-01-02: 58
Project Management | 2017-12-27: 110; 2017-12-28: 39.5; 2017-12-29: 70.5
Leakage | 2017-12-27: 153; 2017-12-28: 0; 2017-12-29: 153; 2017-12-31: 15; 2018-01-01: 138
Regression Testing | 2017-12-27: 37; 2017-12-28: 81; 2017-12-29: 0
Sign Off | 2017-12-27: 0; 2017-12-28: 3; 2017-12-29: 0
Grand Total | 2017-12-27: 1262; 2017-12-28: 575; 2017-12-29: 687
EFFORTS UTILIZATION AS ON 16-May-2018
| APPROVED EFFORTS | PLANNED EFFORTS | ACTUAL EFFORTS | BALANCE EFFORTS
| 575 | 575 | 1262 | -687
Note on AH2: Temp: Bidding Day

## Scenario Prep. & Req. Rework
EFFORTS UTILIZATION DETAILS - SCENARIO PREPARATION & REQUIREMENT REWORK
1. The efforts were utilized fully as the test case preparation approach was Hybrid mode but during review by business the test cases were further detailed further as per the review comments which extended the test cases count from estimated count. Also, there were field level test cases to be written for all fields which was not agreed during estimation and then it was communicated during weekly governance which was written parallelly during round 1 execution as previously no screens/walkthrough of the application shared prior to the round 1 execution start.
2. The estimated count for entire Day1:
| Scope | Functional | Field | Total
| D1/P1 | 7602 | 6265 | 13867
| D1/P2/P3 | 3680 | 2766 | 6446
| Total | 11282 | 9031 | 20313
3. Then during estimation meeting mutually, it was agreed to take hybrid approach after giving 50% reduction on the efforts for preparation front which ideally reduced the count as below:
| Scope | Functional | Field | Total
| D1/P1 | 3801 | 3133 | 6934
| D1/P2/P3 | 1840 | 1383 | 3223
| Total | 5641 | 4516 | 10157
4. The count prepared so far w.r.t. all the journeys on which AQM Team received Signoff on Test Suite
- This test suite got increased due to changes in BRD and inputs from user during Review and Test Suite Walkthrough. | Scope | Functional | Field | Total
- There were approx. 5300 additional test scenarios prepared due to changes in BRD and detailing of the hybrid scenarios in | DAY 01 | 7161 | 8330 | 15491 | Signedoff by Business
further detailing for Business user to signoff test suite. | DAY 02 | 2500 |  | 3300
- Efforts spent for preparation of additional test scenarios (5300/65 = 81 Mandays) but 80 Mandays are chargeable | Total | 9661 | 8330 | 18791
- Refer to the attached embedded file for further details on the BRD versions and test suite submitted/re-submitted versions with multiple rounds of modification
5. The count of day 2 is appearing because while test suite preparation BRD were not having identification of Day 01 and Day 02 hence at the later stage when we received Integration Matrix during February it was classified further into Day 01 and Day 02 and further the integration Matrix GAP was figure out during execution which resulted addition of test cases. E.g. GSTN related BRD was shared after kick start of Direct Sales Execution.
6. The additional 14.5 days was for writing the test cases for the BRDs as mentioned in email subjected "Regarding New BRD Received through Seclore". Dated "Sat 20-01-2018 19:21" Initially this was given as New BRD but this was not new BRDs but process changed in the journeys.

## Round 1 Execution
EFFORTS UTILIZATION DETAILS - TEST SCENARIO EXECUTION ROUND 1
No# | Particulars | TS-Count | Efforts Utilized
1 | Total Execution of In-Scope Test Cases (AQM) | 10157 | 169.2833
2 | Total Execution of In-Scope Test Cases (RHIL-Product Team) - Direct Journey | 778 | 54
3 | Mobility NFR Testing | 126 | 20
| Total Efforts Spent as per Planned Round 1 Execution…. (1) | 11061 | 243.2833
Extra Efforts Spent
4 | Total Execution of Additional added Test Scenarios on the basis of Requirement Rework | 5300 | 88.8333
5 | Additional Scenarios for Testing by RHIL-Product Team for Direct Journey (Loading, Disc., Ref to UW, PPHC Grid, Knock-out) Prep+Exec | 153 | 16
6 | Additional Scenarios for Testing by RHIL-Product Team for Direct Journey (Loading, Disc., Ref to UW, PPHC Grid, Knock-out) Prep+Exec | 80 | 16
Re-executed as part of Round 1 Closure
7 | Total Execution of Test Cases (RHIL-Product Team) - Mobility Journey | 397 | 10
8 | Total Re-Execution of (RHIL-Product Team) - Direct Journey as Round 1 Closure | 380 | 11
9 | Re-Testing of Defects after re-testing of the dependant scenarios for multiple times as on March 2018 | 960 | 50
10 | Efforts utilized for Production Mock Run - Round 1 | 20 | 3
11 | Efforts utilized for Production Mock Run - Defect Retesting | 51 | 3
12 | Testing the system with Business Users separately than the scenarios (ARTL+CHMS+CRM+Customer Portal+DS+Mob+PPHC) |  | 20
13 | Efforts spent for multiple smoke testing for Customer Portal, Direct Sales, Endorsements, Mobility, Underwriting | 250 | 30
14 | Additional efforts spent on Claims testing Tariff based as per the requirement from Dr. Saif (Configuration + Testing) |  | 10
15 | Efforts spent extra due to reduction in productivity due to issues impacting the testing speed as mentioned below |  | 10
- Oops Not Working
- Buttons on the screens not clickable
- Policies not flowing to Underwriting bucket
- Policies not flowing to endorsements
- Something went wrong
- Integration issues where data not flown from one system to another
| Total Additional Efforts spent on Round 1 Execution… (2) |  | 267.8333
| Total Efforts Spent for Round 1 Execution….. (1) + (2) |  | 511.1167

## Round 2 Execution
EFFORTS UTILIZATION DETAILS - TEST SCENARIO EXECUTION ROUND 2
No# | Particulars | TS-Count | Efforts Utilized
1 | Total Execution of In-Scope Test Cases (AQM) | 2300 | 65
2 | Total Execution of In-Scope Test Cases (RHIL-Product Team) - Direct Journey | 98 | 16
3 | Mobility NFR Testing | 63 | 10
| Total Efforts Spent as per Planned Round 1 Execution…. (1) |  | 91
Extra Efforts Spent
4 | Total Execution of Additional added Test Scenarios on the basis of Requirement Rework | 500 | 10
6 | Additional Scenarios for Testing by RHIL-Product Team for Direct Journey (Loading, Disc., Ref to UW, PPHC Grid, Knock-out) Exec | 80 | 5
Re-executed as part of Round 2 Closure
7 | Total Execution of In-Scope Test Cases (RHIL-Product Team) - Mobility Journey | 158 | 10
9 | Re-Testing of Defects after re-testing of the dependant scenarios for multiple times as on March 2018 as Round 2 Closure | 890 | 25
14 | Re-Execution of Entire Test Suite for Communications w.r.t. Template Testing | 1250 | 23
15 | Efforts spent extra due to reduction in productivity due to issues impacting the testing speed as mentioned below |  | 10
- Oops Not Working
- Buttons on the screens not clickable
- Policies not flowing to Underwriting bucket
- Policies not flowing to endorsements
- Something went wrong
- Integration issues where data not flown from one system to another
| Total Additional Efforts spent on Round 1 Execution… (2) |  | 83
| Total Efforts Spent for Round 1 Execution….. (1) + (2) |  | 174

## Leakage Summary
EFFORTS UTILIZATION DETAILS - LEAKAGES
No# | Email Subject | Email Date | Sender | Leakage ManDays
1 | RHIL : : UAT Execution Progress - 21.Feb.2018 | Wed 21-02-2018 19:44 | Kunal | 7
2 | RHIL : : UAT Execution Progress - 22.Feb.2018 | Thu 22-02-2018 19:15 | Kunal | 9
3 | Customer Portal Smoke test Failure | Fri 23-02-2018 18:29 | Krishnan | 5
4 | Customer Portal Smoke test Failure-Failure Date 24/02 | Sat 24-02-2018 12:34 | Krishnan | 5
5 | RE: RHIL : : UAT Execution Progress - 27.Feb.2018 | Tue 27-02-2018 21:34 | Kunal | 8
6 | Smoke Test Failed for Direct Sales | Wed 28-02-2018 22:47 | Kunal | 8
7 | Blocker in Direct Sales Journey | 2018-03-13 15:05 | Urvang | 17
8 | RE: RHIL : : UAT Execution Progress - 19.Mar.2018 | Mon 19-03-2018 20:20 | Kunal | 17
9 | Payment Service Error | 2018-03-21 12:17 | Urvang | 18
10 | RE_ RHIL _ _ UAT Execution Progress - 21_Mar_2018 | Wed 21-03-2018 19:57 | Kunal
11 | UAT Slowness Issue_IRPAS | 2018-04-04 22:08 | Urvang | 14
12 | UAT Slowness Issue_IRPAS | 2018-04-05 09:23 | Urvang
13 | MySalesApp_UAT Issues_10042018 | 2018-04-10 13:28 | Urvang | 8
14 | MySalesApp_Critical Issues_UAT | 2018-04-11 22:29 | Urvang | 14
15 | IRPAS_Unable to Submit UW Decision | 2018-04-11 21:12 | Urvang
16 | RE: RHIL : : UAT Execution Progress - 12.Apr.2018 | Thu 12-04-2018 21:40 | Kunal | 8
17 | Team Ideal due to No defect fixes which resulted to test case execution round 2 | Mon 23-04-2018 | Kunal | 5
18 | Team Ideal due to No defect fixes which resulted to test case execution round 2 | Tue 24-02-2018 | Kunal | 5
19 | Team Ideal due to No defect fixes which resulted to test case execution round 2 | Wed 25-02-2018 | Kunal | 5
| Total Leakages Reported as on 30-Apr-2018 |  |  | 153