## Handover Checklist
HANDOVER CHECKLIST
No# | Handover Category | Project Type | Project Status | Project Domain | Testing Type | Testing Level | Client Name | Activity Name | Primary | Secondary | Handover Status | Date Completed
1 | Project Handover | Fixed Price | Active | Health Insurance | Web+Mobile | Functional | Reliance Health Insurance Limited | Reliance Health Insurance | Urvang | Siva Sir | Completed | 2018-05-24
2 | Project Handover | Fixed Price | Active | Health Insurance | Web+Mobile | Functional+Non-Functional | Reliance Health Insurance Limited | Updated Respository Handover | Urvang | Siva Sir | Completed | 2018-05-24
3 | Project Handover | Fixed Price | Completed | STQC-GIGW | Web | Functional | ARPAN - TCS | STQC Certification Process Followup | Santosh | Ganesh | Completed | 2018-04-10
4 | Project Handover | T&M | Active | General Insurance | Web+Mobile | Functional | New India Assurance | CR Testing | Rohit | Siva Sir | Completed | 2018-04-21
5 | Project Handover | Fixed Price | Completed | General Insurance | Web | Functional | New India Assurance | Respository Handover | Siva Sir |  | Completed | 2018-05-07
6 | Documents Handover | Fixed Price | Completed | General Insurance | Web | Functional | New India Assurance | Signoff Document & SOW, RFP File | Siva Sir |  | Completed | 2018-04-21
7 | Documents Handover | T&M | Completed | General Insurance | Web | Functional | New India Assurance | Preparation of Billing Documents | Rohit | Siva Sir | Completed | 2018-04-21
8 | Project Handover | Fixed Price | Completed | STQC-General | Web | Functional | National eRepositories Limited | Repository Handover - Warehouse Mgmt based project | Santosh | Ganesh | Completed | 2018-04-10
9 | Project Handover | Fixed Price | Completed | Mutual Fund | Mobile | Functional+Non-Functional | Birla Sun Life Asset Management Company | Respository Handover | Santosh | Sandeep | Completed | 2018-05-07
10 | Project Handover | T&M | Active | Mutual Fund | Mobile | Functional+Non-Functional | Birla Sun Life Asset Management Company | Repository is handled by Devendea Bhuwad & Sneha Gupta. Formally activity is to approve timesheet only | Devendra | Sandeep | Completed | 2018-04-10
11 | Project Handover | Fixed Price | Completed | CRM | Web | Functional | Birla Sun Life Asset Management Company | Customer Service (1st Project). Only Repository Handover | Sandeep | Ganesh | Completed | 2018-05-07
12 | Project Handover | Fixed Price | Completed | STQC-eProcurement | Web | Functional | Nextenders | Respository Handover | Santosh | Ganesh | Completed | 2018-04-10
13 | Project Handover | Fixed Price | Completed | STQC-eProcurement | Web | Functional | Nextenders | Recertification Project - Repository Handover | Santosh | Ganesh | Completed | 2018-04-10
14 | Project Handover | Fixed Price | Completed | STQC-eProcurement | Web | Functional | Synise Technologies | Respository Handover | Santosh | Ganesh | Completed | 2018-04-10
15 | Project Handover | Fixed Price | Completed | STQC-General | Web | Functional | NSEIT/DotEx | Respository Handover | Santosh | Ganesh | Completed | 2018-04-10
16 | Project Handover | Fixed Price | Completed | STQC-eProcurement | Web | Functional | MagicBricks | Respository Handover | Santosh | Ganesh | Completed | 2018-04-10
17 | Project Handover | Fixed Price | Completed | Life Insurance | Mobile | Functional | Bharati Axa Life Insurance | Respository Handover | Santosh | Ganesh | Completed | 2018-04-10
18 | Project Handover | Fixed Price | Completed | STQC-eDistrict | Web | Functional | eDistrict Manipur | Respository Handover | Santosh | Ganesh | Completed | 2018-04-10
19 | Project Handover | Internal Project | Active | CMMi | Documentation | Documentation | AQM | CMMi Documentation & Implementation | Santosh |  | Completed | 2018-05-06
20 | Project Handover | Fixed Price | Completed | STQC-General | Web | Functional | HPE-Haryana Police | Respository Handover | Santosh | Ganesh | Completed | 2018-04-10
21 | Project Handover | Fixed Price | Completed | Housing Finance | Mobile | Functional | Edelweiss | Respository Handover | Santosh |  | Completed | 2018-05-07
22 | Project Handover | Fixed Price | Completed | Wealth Management | Mobile | Functional+Non-Functional | Edelweiss | Respository Handover | Santosh | Sandeep | Completed | 2018-05-07
23 | Project Handover | Fixed Price | Completed | Forex | Web | Functional | Essel Finance | Respository Handover | Santosh | Sandeep | Completed | 2018-05-07
24 | Project Handover | Fixed Price | Completed | Mobile Banking | Mobile | Non-Functional | Kotak Mahindra Bank Limites | Respository Handover | Milind | Sandeep | Completed | 2018-05-07
25 | Project Handover | POC | Completed | Mobile Banking | Mobile | Functional+Non-Functional | Federal Bank | Respository Handover | Nishant | Milind Sir | Completed | 2018-04-21
26 | Project Handover | POC | Completed | Life Insurance | Mobile | Functional+Non-Functional | Exide Life Insurance | Respository Handover | Siva Sir |  | Completed | 2018-05-07
27 | Project Handover | Fixed Price | Completed | CapTrustee | Audit | Audit | SBICAPTRUSTEE | Respository Handover | Santosh |  | Completed | 2018-05-07
28 | Project Handover | Fixed Price | Completed | General Insurance | Audit | Audit | ICICI Lombard | Respository Handover | Santosh |  | Completed | 2018-05-07
29 | Project Handover | Fixed Price | Completed | STQC-General | Audit | Audit | Ptechnosoft/Perpetuiti | Respository Handover | Santosh |  | Completed | 2018-05-07
30 | Documents Handover | Internal Project | Completed | Case Study | Documentation | Documentation | Project Case Study | Respository Handover | Santosh |  | Completed | 2018-05-07
31 | Documents Handover | Internal Project | Completed | Estimations | Documentation | Documentation | Project Estimations | Respository Handover | Santosh |  | Completed | 2018-05-07
32 | Training | Internal Training | NA | STQC Process | Classroom Training | Process Training | Training On | Certification Process Documentation | Santosh | Ganesh | Completed | 2018-04-10
33 | Training | Internal Training | NA | Mobile Testing | Classroom Training | Testing Training | Training On | Testing Training | 1) Abhishek Arora 2) Ansu Yadav 3) Utkarsh Bhardwaj 4) Anjali Singh 5) Punam Chavan 6) Gopabandu Pradhan 7) Saket Anand 8) Dineh Markande 9) Gajanan Kasture 10) Suraj 11) Poonam | 1) Nishant 2) Santosh 3) Rajesh Mehta | Completed | 2018-04-07
34 | Training | Internal Training | NA | JIRA Implementation | Classroom Training | Configuration | Training On | Configuration & Implementation | 1) Amar Bhakat 2) Rajesh Bal 3) Ashish Naik 4) Pooja Pingale 5) Anita Rana 6) Karan Singh Rathore 7) Manisha Jain 8) Josy John | 1) Rohit Lanjekar 2) Shaji UK 3) Ganesh Salunkhe 4) Rajesh Mehta 5) Santosh | Completed | 2018-04-10
35 | Documents Handover | Internal Project | Completed | Documentation | Documentation | Documentation | Handover | Supporting Videos + Manual for Customer & Partners | 1) Santosh P 2) Ganesh S 3) Nishant T | 1) Sivadasan R 2) Milind B 3) Sandeep G | Completed | 2018-04-12
36 | Training | Internal Training | NA | TestLink | Classroom Training | Configuration | Training On | Configuration & Implementation | 1) Amar Bhakat 2) Rajesh Bal 3) Ashish Naik 4) Pooja Pingale 5) Anita Rana 6) Karan Singh Rathore 7) Manisha Jain 8) Josy John | 1) Rohit Lanjekar 2) Shaji UK 3) Ganesh Salunkhe 4) Rajesh Mehta 5) Santosh | Completed | 2018-04-10
37 | Documents Handover | Internal Project | Completed | Documentation | Documentation | Documentation | Handover | Preparation of Billing Documents | Rohit Lanjekar | Siva Sir | Completed | 2018-04-21